## Sources of Risk
Sources of Risk
Characteristic | Key feature perceived
Unclear purpose | Lack of a clear understanding of why the sponsor is implementing the change
No need | Do not share the sponsor’s belief in the need for change
Not involved | Lack of ownership for changes that people have not provided or contributed to
Poor communication | There has been little, clear communication leading to distortion
Cost too high | The physical, intellectual or emotional price to change is high
Inadequate reward | Do not believe that the change and disruption warrant the proposal
Incompatible change | People view the proposed changes as incompatible with the society
Low management commitment | Do not believe senior management are genuinely committed to changes
Adverse social impact | The change will have an adverse effect on their social relations
Inadequate support | People do not believe sufficient time, money and commitment will be made available
Inappropriate change rate | Seen as too fast or too slow
Habits ignored | Current work patterns and habits ignored
Decreased autonomy | Control over own jobs is diminished
Change fatigue | Yet another poorly managed initiative
Failure fear | Real risk of the changes not being achieved
Status quo contentment | Happy with the current situation
Low implementation skills | Do not possess the change skills required
Change agent distrust | Lack of respect/trust in change agents and therefore the changes
Excessive pressure | Already under pressure from current activity
Vested interests | Changes are driven by hidden agendas
Prestige challenged | Challenge status, salary or prestige
Goal incompatibility | Society and personal objectives don’t match
No going back | High risk as changes cannot be reversed
Past failure acknowledgement | Required to acknowledge past failures

## Risk Assesment Matrix
Risk Assessment Matrix
[7 empty] | Minor Risk | Major Risk
Instructions: Identify to the risks to which the change project could be exposed. Score the impact and probability using the scale below: Impact Scoring Probability Scoring severe to critical = 3 probable = 3 significant to high = 2 possible = 2 minor to moderate = 1 remote/unlikely = 1 Create a mitigation plan to address the risk.
[7 empty] | Signficant Risk | Maximum Risk
No | Risk Description | Impact | Probability | Mitigation | Impact | Probability
A |  | 3 | 3 |  | 2.8511 | 2.9197
B |  | 3 | 2 |  | 3.0671 | 2.2039
C |  | 3 | 1 |  | 2.9627 | 1.2298
D |  | 1 | 3 |  | 1.2249 | 3.2427
E |  | 1 | 2 |  | 0.94965 | 2.0231
F |  | 1 | 1 |  | 1.082 | 1.164
G |  | 2 | 3 |  | 1.8612 | 2.9423
H |  | 2 | 2 |  | 2.0477 | 1.9344
I |  | 2 | 1 |  | 2.174 | 1.0874
J |  |  |  |  | -1 | -1
K |  |  |  |  | -1 | -1
L |  |  |  |  | -1 | -1
M |  |  |  |  | -1 | -1
N |  |  |  |  | -1 | -1
O |  |  |  |  | -1 | -1
P |  |  |  |  | -1 | -1
Q |  |  |  |  | -1 | -1
R |  |  |  |  | -1 | -1
S |  |  |  |  | -1 | -1
T |  |  |  |  | -1 | -1
U |  |  |  |  | -1 | -1
V |  |  |  |  | -1 | -1
W |  |  |  |  | -1 | -1
X |  |  |  |  | -1 | -1
Y |  |  |  |  | -1 | -1
Impact
Probability